## Projects
id | name | start_date | deadline | status
1 | AI Project Monitoring Tool | 2026-09-22 | 2026-09-24 | active

## Team Members
id | name | weekly_capacity_hours | current_allocated_hours | skills
1 | Priya Nair | 40 | 31 | python,sql,flask
2 | Jonas Weber | 40 | 0 | python,power-bi,power-automate
3 | Amara Okafor | 32 | 13 | scada,iiot,python
4 | Liu Chen | 40 | 5 | sql,power-bi,excel
5 | Marco Rossi | 20 | 18 | flask,react,ui-design

## Tasks
id | project_id | title | assignee_id | estimated_hours | logged_hours | due_date | dependency_ids | status | comment_text | required_skills
1 | 1 | Design database schema | 1 | 6 | 5.9 | 2026-09-27 |  | Blocked | Blocked - waiting on the API contract from the backend team. | sql,python
2 | 1 | Build task CRUD API | 1 | 10 | 8.7 | 2026-09-22 |  | Done | On track, no issues. | python,flask
3 | 1 | Build team member CRUD API | 1 | 6 | 6.1 | 2026-09-27 |  | In Progress |  | python,flask
4 | 1 | Generate synthetic dataset | 5 | 4 | 3.1 | 2026-09-24 |  | In Progress | Started work, looks straightforward. | python,sql
5 | 1 | Build dashboard skeleton | 1 | 8 | 9.4 | 2026-09-25 |  | To Do | Started work, looks straightforward. | python,power-bi
6 | 1 | Build manual entry form UI | 5 | 6 | 3.5 | 2026-09-27 |  | Blocked | Blocked - waiting on the API contract from the backend team. | python,flask,ui-design
7 | 1 | Build risk-scoring formula | 1 | 6 | 7.1 | 2026-09-22 |  | To Do | Started work, looks straightforward. | python,sql
8 | 1 | Train risk classifier | 1 | 5 | 3.4 | 2026-09-22 |  | To Do |  | python
9 | 1 | Build workload utilization calc | 3 | 5 | 6.8 | 2026-09-28 |  | Blocked | Blocked on a dependency, can't proceed until it's resolved. | python,sql
10 | 1 | Build reallocation engine | 3 | 6 | 7.6 | 2026-09-25 |  | To Do |  | python,sql
11 | 1 | Build skill-matching engine | 4 | 5 | 4.1 | 2026-09-26 |  | In Review |  | python,sql
12 | 1 | Wire risk heatmap into UI | 5 | 4 | 4.8 | 2026-09-24 |  | In Review |  | python,react,ui-design
13 | 1 | Wire workload chart into UI | 5 | 4 | 4 | 2026-09-25 |  | Done | Started work, looks straightforward. | python,react,ui-design
14 | 1 | Write integration tests | 5 | 4 | 4.7 | 2026-09-22 | 7 | In Progress | On track, no issues. | python
15 | 1 | Write README and demo script | 3 | 2 | 1.9 | 2026-09-25 |  | In Review |  | python

## Risk Scores
task_id | score | factors | computed_at

## Reallocation Suggestions
id | from_member_id | to_member_id | task_id | reason

## Assignment Suggestions
id | task_id | candidate_member_id | match_score | reason